## Sheet1
Work Breakdown Structure |  |  |  |  | Analytic Platform
Level | WBS | Task Description | Assigned To | Duration(days) | Notes | started | end
1 | 1 | Phase 1: Implement Basic functions for Web analytic platform
2 | 1.1 | JS tracking
3 | 1.1.1 | Generate _fsa cookie |  | 0.5 |  | 2017-11-08 | 2017-11-08
3 | 1.1.2 | Generate _fsid cookie |  | 0.5 |  | 2017-11-08 | 2017-11-08
3 | 1.1.3 | Create single tracker |  | 2 |  | 2017-11-09 | 2017-11-09
3 | 1.1.4 | Get basic information for page tracking (page view) |  | 10 |  | 2017-11-13
2 | 1.2 | Kafka Message Queue
3 | 1.2.1 | Setup Kafka |  | 0.5
3 | 1.2.2 | Test Kafka ( create topic test and pub/sub data)
4 | 1.2.2.1 | Publish\Subcribe from command line to "test" topic |  | 1
3 | 1.2.3 | Design Kafka Topic for log data |  | 5
2 | 1.3 | Spark - Setup & integrate to Kafka
3 | 1.3.1 | Setup spark |  | 0.5
3 | 1.3.2 | Get data from kafka topic |  | 3
2 | 1.4 | Cassandra database - Setup, intergrate, test
3 | 1.4.1 | Setup cassandra |  | 0.5
3 | 1.4.2 | Integrate to Django |  | 2
3 | 1.4.3 | Test to read\write data |  | 2
2 | 1.5 | Frontend
3 | 1.5.1 | Design simple dashboard with bootstrap & Django |  | 15
4 | 1.5.1.1 | User login function |  | 1
4 | 1.5.1.2 | Dashboard for user/session (tab style) with line chart |  | 2
4 | 1.5.1.3 | Dashboard for session by devices |  | 3
4 | 1.5.1.4 | Dashboard for user right now with counter & column bar |  | 2
4 | 1.5.1.5 | Dashboard for views of each page |  | 2
4 | 1.5.1.6 | Dashboard for Geolocation |  | 4
4 | 1.5.1.7 | Dashboard for active user (line chart for weekly/Daily) |  | 1
3 | 1.5.2 | Get data from database/spark |  | 5
2 | 1.6 | Spark - Processing
3 | 1.6.1 | Determine archieved data |  | 3
3 | 1.6.2 | Process to create archive data |  | 4
2 | 1.7 | Backend
3 | 1.7.1 | Setup Django project base django-admin |  | 0.5
3 | 1.7.2 | Determine IP location (for IP v4)
4 | 1.7.2.1 | Setup & integrate MaxMind GeoIP database |  | 0.5
4 | 1.7.2.2 | Extract IP from gif request and find location from GeoIP database |  | 2
3 | 1.7.3 | Create Django's Middleware for Kafka publish to "test" topic |  | 4
2 | 1.8 | Cassandra database - Basic build for Analytic platform
3 | 1.8.1 | Determine basic objects for Analytic platform |  | 2
3 | 1.8.2 | Design database |  | 5
3 | 1.8.3 | Test database |  | 3
1 | 2 | Phase 2
1 | 3 | Phase 3
71.5